## Cover
CAFE
Group 2
| Creator |  | Aung Kaung Moe Chit Paing Soe Ei Pwint Phyo Chyu Yati Win Myat Thwe
| Create Date |  | 2023-02-27
| Last Update Date |  | 2023-04-09
| Role | AKM | CPS | EPP | CY | WMT
| Front End | ● | ● | ● | ● | ●
| Backend | ● |  | ● |  | ●
Company Co., Ltd

## Schedule (Task)
Schedule | CAFE | [9 empty] | Create Date | 2023-02-27
[11 empty] | Update Date | 2023-03-10
| No | Sub | Task | Assign | Estimate Start | Estimate End | Duration | Actual Start | Actual End | Duration | Complete %
| 1 |  | Schedule | ALL | 2023-02-27 | 2023-03-29 | 30 | 2023-02-27 | 2023-04-08 | 40 | 0%
| 2 |  | Japanese Translation | CPS | 2023-03-06 | 2023-03-11 | 5 | 2023-03-06 | 2023-03-11 | 5 | 90%
| 3 |  | Logo Design | CY | 2023-02-27 | 2023-02-28 | 1 | 2023-02-27 | 2023-02-28 | 1 | 100%
| 4 |  | Requirement Definition | WMT | 2023-02-27 | 2023-02-28 | 1 | 2023-02-27 | 2023-02-28 | 1 | 100%
| 5 |  | Function List | AKM,EPP,WMT | 2023-02-28 | 2023-03-01 | 1 | 2023-02-28 | 2023-03-01 | 1 | 100%
| 6 |  | User
|  | 6-1 | Screen List | AKM,EPP,WMT | 2023-02-27 | 2023-02-28 | 1 | 2023-02-27 | 2023-02-28 | 1 | 100%
|  | 6-2 | UI/UX Kit | AKM,EPP | 2023-02-28 | 2023-03-01 | 1 | 2023-02-28 | 2023-03-01 | 1 | 100%
|  | 6-3 | User Screen Flow | AKM,CY | 2023-02-27 | 2023-02-28 | 1 | 2023-02-27 | 2023-02-28 | 1 | 100%
Figma
|  | 6-4 | Home Page | AKM | 2023-02-28 | 2023-03-01 | 1 | 2023-02-28 | 2023-03-01 | 1 | 100%
|  | 6-5 | Login | EPP | 2023-03-01 | 2023-03-02 | 1 | 2023-03-01 | 2023-03-02 | 1 | 100%
|  | 6-6 | Sign Up | EPP | 2023-03-01 | 2023-03-02 | 1 | 2023-03-01 | 2023-03-02 | 1 | 100%
|  | 6-7 | Forget password (getOTP) | EPP | 2023-03-01 | 2023-03-02 | 1 | 2023-03-01 | 2023-03-02 | 1 | 100%
|  | 6-8 | Forget password (change password) | EPP | 2023-03-01 | 2023-03-02 | 1 | 2023-03-01 | 2023-03-02 | 1 | 100%
|  | 6-9 | Promotion page | CY,CPS | 2023-03-05 | 2023-03-06 | 1 | 2023-03-05 | 2023-03-06 | 1 | 100%
|  | 6-10 | Buy Shop | AKM | 2023-03-01 | 2023-03-02 | 1 | 2023-03-01 | 2023-03-02 | 1 | 100%
|  | 6-11 | Shop Payment | AKM | 2023-03-01 | 2023-03-02 | 1 | 2023-03-01 | 2023-03-02 | 1 | 100%
|  | 6-12 | Blog Page | AKM | 2023-03-01 | 2023-03-02 | 1 | 2023-03-01 | 2023-03-02 | 1 | 100%
|  | 6-13 | Shop Interface | EPP | 2023-03-01 | 2023-03-02 | 1 | 2023-03-01 | 2023-03-02 | 1 | 100%
|  | 6-14 | User Profile(Dashboard) | CY,CPS | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 6-15 | Favourite List | CY,CPS | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 6-16 | Booking(Dashboard) | CPS | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 6-17 | Order Page (Dashboard) | CY | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 6-18 | Chat Box(Dashboard) | CY,CPS | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 6-19 | Shop List | CPS | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 6-20 | Booking Page | EPP | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 6-21 | Order Page | EPP | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 6-22 | User Guide | WMT | 2023-03-05 | 2023-03-06 | 1 | 2023-03-05 | 2023-03-06 | 1 | 100%
|  | 6-23 | Privacy & Policy | EPP | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 6-24 | Log out Popup | EPP | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 6-25 | FAQs | WMT | 2023-03-05 | 2023-03-06 | 1 | 2023-03-05 | 2023-03-06 | 1 | 100%
|  | 6-26 | search | AKM | 2023-03-05 | 2023-03-06 | 1 | 2023-03-05 | 2023-03-06 | 1 | 100%
|  | 6-27 | WavePayment(4Step) Page-1 | AKM | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 6-28 | WavePayment(4Step) Page-2 | AKM | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 6-29 | WavePayment(4Step) Page-3 | AKM | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 6-30 | WavePayment(4Step) Page-4 | AKM | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 6-31 | Cart (PopUp) | EPP | 2023-03-05 | 2023-03-06 | 1 | 2023-03-05 | 2023-03-06 | 1 | 100%
|  | 6-32 | Checkout(PopUp) | EPP | 2023-03-05 | 2023-03-06 | 1 | 2023-03-06 | 2023-03-07 | 1 | 100%
|  | 6-33 | OrderConfirm(PopUp) | EPP | 2023-03-06 | 2023-03-06 | 1 | 2023-03-06 | 2023-03-07 | 1 | 100%
|  | 6-34 | Favourite List(PopUp) | AKM | 2023-03-06 | 2023-03-07 | 1 | 2023-03-06 | 2023-03-07 | 1 | 100%
|  | 6-35 | Confirm(PopUp) | EPP | 2023-03-06 | 2023-03-07 | 1 | 2023-03-06 | 2023-03-06 | 1 | 100%
|  | 6-36 | KBZPayment(QRcode) | AKM | 2023-03-07 | 2023-03-08 | 1 | 2023-03-07 | 2023-03-08 | 1 | 100%
|  | 6-37 | Payment Successful | AKM | 2023-03-07 | 2023-03-08 | 1 | 2023-03-07 | 2023-03-08 | 1 | 100%
|  | 6-38 | Seemore(cafe&cakesmenu) | CY | 2023-03-06 | 2023-03-06 | 1 | 2023-03-07 | 2023-03-08 | 1 | 100%
|  | 6-39 | Seemore(shop) | CY | 2023-03-07 | 2023-03-08 | 1 | 2023-03-07 | 2023-03-08 | 1 | 100%
|  | 6-40 | PromotionSeemore(cafe&cakes) | CY | 2023-03-08 | 2023-03-08 | 1 | 2023-03-08 | 2023-03-08 | 1 | 100%
|  | 6-41 | PromotionSeemore(shop) | CY | 2023-03-06 | 2023-03-06 | 1 | 2023-03-06 | 2023-03-06 | 1 | 100%
|  | 6-42 | Menu(ShopInterface) | EPP | 2023-02-07 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 6-43 | Reviews(Dashboard) | CPS | 2023-03-08 | 2023-03-09 | 2 | 2023-03-08 | 2023-03-09 | 2 | 100%
|  | 6-44 | Setting(Dashboard) | CPS | 2023-03-08 | 2023-03-09 | 2 | 2023-03-08 | 2023-03-09 | 2 | 100%
|  | 6-48 | dashboard(notification) | AKM | 2023-03-06 | 2023-03-07 | 1 | 2023-03-06 | 2023-03-07 | 1 | 100%
| 7 |  | Shop
|  | 7-1 | Screen List | AKM,EPP,CY | 2023-02-27 | 2023-02-28 | 1 | 2023-02-27 | 2023-02-28 | 1 | 100%
|  | 7-2 | Shop Screen Flow | WMT | 2023-02-28 | 2023-03-01 | 1 | 2023-02-28 | 2023-03-01 | 1 | 100%
Figma
|  | 7-3 | Login | EPP | 2023-03-01 | 2023-03-02 | 1 | 2023-03-01 | 2023-03-02 | 1 | 100%
|  | 7-4 | sale chart | AKM | 2023-03-03 | 2023-03-04 | 1 | 2023-03-03 | 2023-03-04 | 1 | 100%
|  | 7-5 | Forget Password(get OTP) | EPP | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 7-6 | Forget password (change password) | EPP | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 7-7 | History | AKM | 2023-03-03 | 2023-03-04 | 1 | 2023-03-03 | 2023-03-04 | 1 | 100%
|  | 7-8 | Order Page | AKM | 2023-03-03 | 2023-03-04 | 1 | 2023-03-03 | 2023-03-04 | 1 | 100%
|  | 7-9 | Booking | AKM | 2023-03-03 | 2023-03-04 | 1 | 2023-03-03 | 2023-03-04 | 1 | 100%
|  | 7-10 | Change Information | AKM | 2023-03-03 | 2023-03-04 | 1 | 2023-03-03 | 2023-03-04 | 1 | 100%
|  | 7-11 | Add & Change Blog | AKM | 2023-03-03 | 2023-03-04 | 1 | 2023-03-03 | 2023-03-04 | 1 | 100%
|  | 7-12 | Add & Change Menu | AKM | 2023-03-03 | 2023-03-04 | 1 | 2023-03-03 | 2023-03-04 | 1 | 100%
|  | 7-13 | Message Chart Box | AKM | 2023-03-03 | 2023-03-04 | 1 | 2023-03-03 | 2023-03-04 | 1 | 100%
|  | 7-14 | Discount & Promotion | AKM | 2023-03-03 | 2023-03-04 | 1 | 2023-03-03 | 2023-03-04 | 1 | 100%
|  | 7-15 | Renewal Shop | AKM | 2023-03-03 | 2023-03-04 | 1 | 2023-03-03 | 2023-03-04 | 1 | 100%
|  | 7-16 | notification | AKM | 2023-03-03 | 2023-03-04 | 1 | 2023-03-03 | 2023-03-04 | 1 | 100%
|  | 7-17 | Gallery | AKM | 2023-03-03 | 2023-03-04 | 1 | 2023-03-03 | 2023-03-04 | 1 | 100%
|  | 7-18 | menu | AKM | 2023-03-03 | 2023-03-04 | 1 | 2023-03-03 | 2023-03-04 | 1 | 100%
|  | 7-19 | Theme | AKM | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 7-20 | update menu | AKM | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 7-21 | gallery | EPP | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
| 8 |  | Admin
|  | 8-1 | Screen List | AKM,EPP,CY,WMT | 2023-02-27 | 2023-02-28 | 1 | 2023-02-27 | 2023-02-28 | 1 | 100%
|  | 8-2 | Admin Screen Flow | CY | 2023-02-27 | 2023-02-28 | 1 | 2023-02-27 | 2023-02-28 | 1 | 100%
Figma
|  | 8-3 | Shop List (Dashboard) | WMT | 2023-03-02 | 2023-03-03 | 1 | 2023-03-02 | 2023-03-03 | 1 | 100%
|  | 8-4 | Login | EPP | 2023-03-02 | 2023-03-03 | 1 | 2023-03-02 | 2023-03-03 | 1 | 100%
|  | 8-5 | User List (Dashboard) | WMT | 2023-03-02 | 2023-03-04 | 2 | 2023-03-02 | 2023-03-04 | 2 | 100%
|  | 8-6 | Message Chat Box (Dashboard) | WMT | 2023-03-02 | 2023-03-04 | 2 | 2023-03-02 | 2023-03-04 | 2 | 100%
|  | 8-7 | Home Slider (Dashboard) | WMT | 2023-03-02 | 2023-03-04 | 2 | 2023-03-02 | 2023-03-04 | 2 | 100%
|  | 8-8 | About (Dashboard) | WMT | 2023-03-02 | 2023-03-04 | 2 | 2023-03-02 | 2023-03-04 | 2 | 100%
|  | 8-9 | Service (Dashboard) | WMT | 2023-03-02 | 2023-03-04 | 2 | 2023-03-02 | 2023-03-04 | 2 | 100%
|  | 8-10 | Customer's Review (Dashboard) | WMT | 2023-03-02 | 2023-03-04 | 2 | 2023-03-02 | 2023-03-04 | 2 | 100%
|  | 8-11 | Choose options & fill | WMT | 2023-03-04 | 2023-03-05 | 1 | 2023-03-04 | 2023-03-05 | 1 | 100%
|  | 8-12 | Contact Us (Dashboard) | WMT | 2023-03-02 | 2023-03-04 | 2 | 2023-03-02 | 2023-03-04 | 2 | 100%
|  | 8-13 | Theme & Font (Dashboard) | WMT | 2023-03-02 | 2023-03-04 | 2 | 2023-03-02 | 2023-03-04 | 2 | 100%
|  | 8-14 | Privacy & Policy(Dashboard) | WMT | 2023-03-02 | 2023-03-04 | 2 | 2023-03-02 | 2023-03-04 | 2 | 100%
|  | 8-15 | FAQs(Dashboard) | WMT | 2023-03-05 | 2023-03-06 | 1 | 2023-03-05 | 2023-03-06 | 1 | 100%
|  | 8-16 | Discount & Promotions (Page 1) | WMT | 2023-03-06 | 2023-03-07 | 1 | 2023-03-06 | 2023-03-07 | 1 | 100%
|  | 8-17 | Discount & Promotions (Page 2) | WMT | 2023-03-07 | 2023-03-08 | 1 | 2023-03-07 | 2023-03-08 | 1 | 100%
|  | 8-18 | Footer | WMT | 2023-03-08 | 2023-03-09 | 1 | 2023-03-02 | 2023-03-04 | 2 | 100%
|  | 8-19 | Order List(Dashboard) | AKM | 2023-03-08 | 2023-03-09 | 1 | 2023-03-02 | 2023-03-04 | 1 | 100%
| 9 |  | Database Design | CY,WMT | 2023-03-07 | 2023-03-11 | 4 | 2023-03-07 | 2023-03-11 | 4 | 100%
| 10 |  | ER Diagram | CY,WMT | 2023-03-10 | 2023-03-11 | 1 | 2023-03-10 | 2023-03-11 | 1 | 100%
| 11 |  | Frontend
User
|  | 11-1 | Home Page | AKM | 2023-03-11 | 2023-03-13 | 2 | 2023-03-11 | 2023-03-13 | 2 | 100%
|  | 11-2 | Login | EPP | 2023-03-12 | 2023-03-13 | 1 | 2023-03-12 | 2023-03-13 | 1 | 100%
|  | 11-3 | Sign Up | EPP | 2023-03-12 | 2023-03-13 | 1 | 2023-03-12 | 2023-03-13 | 1 | 100%
|  | 11-4 | Forget password (getOTP) | EPP | 2023-03-12 | 2023-03-13 | 1 | 2023-03-12 | 2023-03-13 | 1 | 100%
|  | 11-5 | Forget password (change password) | EPP | 2023-03-12 | 2023-03-13 | 1 | 2023-03-12 | 2023-03-13 | 1 | 100%
|  | 11-6 | Promotion shop&product | CY | 2023-03-14 | 2023-03-15 | 1 | 2023-03-13 | 2023-03-16 | 3 | 100%
|  | 11-7 | Promotion product menu | CY | 2023-03-15 | 2023-03-15 | 0 | 2023-03-15 | 2023-03-15 | 0 | 100%
|  | 11-8 | Promotion Shop menu | CY | 2023-03-16 | 2023-03-16 | 0 | 2023-03-16 | 2023-03-16 | 0 | 100%
|  | 11-9 | Buy Shop | AKM | 2023-03-13 | 2023-03-14 | 1 | 2023-03-13 | 2023-03-14 | 1 | 100%
|  | 11-10 | Blog Page | AKM | 2023-03-14 | 2023-03-15 | 1 | 2023-03-13 | 2023-03-14 | 1 | 100%
|  | 11-11 | buyShopFillInformation | AKM | 2023-03-13 | 2023-03-14 | 1 | 2023-03-13 | 2023-03-14 | 1 | 100%
|  | 11-12 | User Profile(Dashboard) | CPS | 2023-03-12 | 2023-03-18 | 6 | 2023-03-13 | 2023-03-14 | 1 | 100%
|  | 11-13 | Favourite List | AKM | 2023-03-13 | 2023-03-14 | 1 | 2023-03-13 | 2023-03-14 | 1 | 100%
|  | 11-14 | Booking(Dashboard) | CPS | 2023-03-12 | 2023-03-18 | 6 |  |  | 0 | 100%
|  | 11-15 | Order Page (Dashboard) | CPS | 2023-03-12 | 2023-03-18 | 6 | 2023-03-13 | 2023-03-14 | 1 | 100%
|  | 11-16 | Chat Box(Dashboard) | CPS | 2023-03-12 | 2023-03-18 | 6 |  |  | 0 | 100%
|  | 11-17 | Shop List | CY | 2023-03-17 | 2023-03-17 | 0 | 2023-03-16 | 2023-03-17 | 1 | 100%
|  | 11-18 | Booking Page | EPP | 2023-03-16 | 2023-03-17 | 1 | 2023-03-14 | 2023-03-15 | 1 | 100%
|  | 11-19 | Order Page | AKM | 2023-03-26 | 2023-03-27 | 1 | 2023-03-27 | 2023-03-28 | 1 | 100%
|  | 11-20 | Privacy & Policy | WMT | 2023-03-12 | 2023-03-13 | 1 | 2023-03-12 | 2023-03-13 | 1 | 100%
|  | 11-21 | Log out Popup | WMT | 2023-03-17 | 2023-03-18 | 1 | 2023-03-17 | 2023-03-18 | 1 | 100%
|  | 11-22 | FAQs | WMT | 2023-03-12 | 2023-03-13 | 1 | 2023-03-12 | 2023-03-13 | 1 | 100%
|  | 11-23 | WavePayment(4Step) Page-1 | EPP | 2023-03-14 | 2023-03-15 | 1 | 2023-03-15 | 2023-03-16 | 1 | 100%
|  | 11-24 | WavePayment(4Step) Page-2 | EPP | 2023-03-14 | 2023-03-15 | 1 | 2023-03-15 | 2023-03-16 | 1 | 100%
|  | 11-25 | WavePayment(4Step) Page-3 | EPP | 2023-03-14 | 2023-03-15 | 1 | 2023-03-15 | 2023-03-16 | 1 | 100%
|  | 11-26 | WavePayment(4Step) Page-4 | EPP | 2023-03-14 | 2023-03-15 | 1 | 2023-03-15 | 2023-03-16 | 1 | 100%
|  | 11-27 | Cart (PopUp) | EPP | 2023-03-16 | 2023-03-17 | 1 | 2023-03-16 | 2023-03-17 | 1 | 100%
|  | 11-28 | Checkout(PopUp) | EPP | 2023-03-14 | 2023-03-15 | 1 | 2023-03-14 | 2023-03-19 | 5 | 100%
|  | 11-29 | OrderConfirm | AKM | 2023-03-13 | 2023-03-14 | 1 | 2023-03-13 | 2023-03-14 | 1 | 100%
|  | 11-30 | Confirm(PopUp) | WMT | 2023-03-12 | 2023-03-18 | 6 | 2023-03-19 | 2023-03-20 | 1 | 100%
|  | 11-31 | KBZPayment | WMT | 2023-03-12 | 2023-03-18 | 6 | 2023-03-19 | 2023-03-20 | 1 | 100%
|  | 11-32 | Payment Successful | WMT | 2023-03-12 | 2023-03-18 | 6 | 2023-03-19 | 2023-03-20 | 1 | 100%
|  | 11-33 | PromotionSeemore(cafe&cakes) | CY,CPS | 2023-03-14 | 2023-03-17 | 3 | 2023-03-14 | 2023-03-17 | 3 | 100%
|  | 11-34 | Menu(ShopInterface) | EPP | 2023-03-16 | 2023-03-17 | 1 | 2023-03-16 | 2023-03-17 | 1 | 100%
|  | 11-35 | Reviews(Dashboard) | CPS | 2023-03-12 | 2023-03-18 | 6 | 2023-03-17 | 2023-03-18 | 1 | 100%
|  | 11-36 | Setting(Dashboard) | CPS | 2023-03-12 | 2023-03-18 | 6 | 2023-03-18 | 2023-03-19 | 1 | 100%
|  | 11-37 | UserGuide | WMT | 2023-04-08 | 2023-04-09 | 1 | 2023-04-08 | 2023-04-09 | 1 | 100%
|  | 11-38 | seemore(cafe&cakesmenu) | AKM | 2023-03-20 | 2023-03-21 | 1 | 2023-03-20 | 2023-03-21 | 1 | 100%
|  | 11-39 | Booking | EPP | 2023-03-15 | 2023-03-16 | 1 | 2023-03-15 | 2023-03-16 | 1 | 100%
| 12 |  | Shop
|  | 12-1 | Login | EPP | 2023-03-12 | 2023-03-13 | 1 | 2023-03-12 | 2023-03-13 | 1 | 100%
|  | 12-2 | sale chart | AKM | 2023-03-16 | 2023-03-17 | 1 | 2023-03-16 | 2023-03-17 | 1 | 100%
|  | 12-3 | Forget Password(get OTP) | EPP | 2023-03-12 | 2023-03-13 | 1 | 2023-03-12 | 2023-03-13 | 1 | 100%
|  | 12-4 | Forget password (change password) | EPP | 2023-03-12 | 2023-03-13 | 1 | 2023-03-12 | 2023-03-13 | 1 | 100%
|  | 12-5 | History | AKM | 2023-03-14 | 2023-03-15 | 1 | 2023-03-14 | 2023-03-15 | 1 | 100%
|  | 12-6 | Order Page | AKM | 2023-03-14 | 2023-03-15 | 1 | 2023-03-14 | 2023-03-15 | 1 | 100%
|  | 12-7 | Booking | AKM | 2023-03-14 | 2023-03-15 | 1 | 2023-03-14 | 2023-03-15 | 1 | 100%
|  | 12-8 | Change Information | AKM | 2023-03-16 | 2023-03-17 | 1 | 2023-03-15 | 2023-03-16 | 1 | 100%
|  | 12-9 | Add & Change Blog | AKM | 2023-03-16 | 2023-03-17 | 1 | 2023-03-15 | 2023-03-16 | 1 | 100%
|  | 12-10 | Add & Change Menu | AKM | 2023-03-16 | 2023-03-17 | 1 | 2023-03-19 | 2023-03-20 | 1 | 100%
|  | 12-11 | Message Chat Box | AKM | 2023-03-17 | 2023-03-18 | 1 | 2023-03-17 | 2023-03-18 | 1 | 100%
|  | 12-12 | Discount & Promotion | AKM | 2023-03-16 | 2023-03-17 | 1 | 2023-03-15 | 2023-03-16 | 1 | 100%
|  | 12-13 | Renewal Shop | AKM | 2023-03-16 | 2023-03-16 | 0 | 2023-03-15 | 2023-03-16 | 1 | 100%
|  | 12-14 | Notification | AKM | 2023-03-17 | 2023-03-18 | 1 | 2023-03-15 | 2023-03-16 | 1 | 100%
|  | 12-15 | Gallery | AKM | 2023-03-17 | 2023-03-18 | 1 | 2023-03-15 | 2023-03-16 | 1 | 100%
|  | 12-16 | Menu | AKM | 2023-03-17 | 2023-03-18 | 1 | 2023-03-17 | 2023-03-18 | 1 | 100%
|  | 12-17 | Theme | AKM | 2023-03-17 | 2023-03-18 | 1 | 2023-03-17 | 2023-03-18 | 1 | 100%
|  | 12-18 | Shop Guide | WMT | 2023-04-08 | 2023-04-09 | 1 | 2023-04-08 | 2023-04-09 | 1 | 100%
| 13 |  | Admin
|  | 13-1 | Shop List (Dashboard) | WMT | 2023-03-12 | 2023-03-18 | 6 | 2023-03-17 | 2023-03-18 | 1 | 100%
|  | 13-2 | Login | EPP | 2023-03-12 | 2023-03-13 | 1 | 2023-03-12 | 2023-03-13 | 1 | 100%
|  | 13-3 | User List (Dashboard) | WMT | 2023-03-12 | 2023-03-18 | 6 | 2023-03-17 | 2023-03-18 | 1 | 100%
|  | 13-4 | Message Chat Box (Dashboard) | AKM | 2023-03-12 | 2023-03-18 | 6 | 2023-03-17 | 2023-03-18 | 1 | 100%
|  | 13-5 | Home Slider (Dashboard) | WMT | 2023-03-12 | 2023-03-18 | 6 | 2023-03-16 | 2023-03-17 | 1 | 100%
|  | 13-6 | About (Dashboard) | WMT | 2023-03-12 | 2023-03-18 | 6 | 2023-03-16 | 2023-03-17 | 1 | 100%
|  | 13-7 | Service (Dashboard) | WMT | 2023-03-12 | 2023-03-18 | 6 | 2023-03-16 | 2023-03-17 | 1 | 100%
|  | 13-8 | Customer's Review (Dashboard) | WMT | 2023-03-12 | 2023-03-18 | 6 | 2023-03-17 | 2023-03-18 | 1 | 100%
|  | 13-9 | Choose options & fill | AKM | 2023-03-12 | 2023-03-18 | 6 | 2023-03-17 | 2023-03-18 | 1 | 100%
|  | 13-10 | Contact Us (Dashboard) | WMT | 2023-03-12 | 2023-03-18 | 6 | 2023-03-16 | 2023-03-17 | 1 | 100%
|  | 13-11 | Theme & Font (Dashboard) | WMT | 2023-03-12 | 2023-03-18 | 6 | 2023-03-17 | 2023-03-18 | 1 | 100%
|  | 13-12 | PrivacyPolicy(Dashboard) | WMT | 2023-03-12 | 2023-03-18 | 6 | 2023-03-16 | 2023-03-17 | 1 | 100%
|  | 13-13 | FAQs(Dashboard) | WMT | 2023-03-12 | 2023-03-18 | 6 | 2023-03-16 | 2023-03-17 | 1 | 100%
|  | 13-14 | Discount & Promotions (Page 1) | WMT | 2023-03-12 | 2023-03-18 | 6 | 2023-03-16 | 2023-03-17 | 1 | 100%
|  | 13-15 | Discount & Promotions (Page 2) | WMT | 2023-03-12 | 2023-03-18 | 6 | 2023-03-16 | 2023-03-17 | 1 | 100%
|  | 13-16 | Footer | WMT | 2023-03-12 | 2023-03-18 | 6 | 2023-03-16 | 2023-03-17 | 1 | 100%
| 14 |  | Backend
User
|  | 14-1 | Login | EPP | 2023-03-20 | 2023-03-21 | 1 | 2023-03-23 | 2023-03-24 | 1 | 100%
|  | 14-2 | Sign Up/ register | EPP | 2023-03-21 | 2023-03-22 | 1 | 2023-03-21 | 2023-03-23 | 3 | 100%
|  | 14-3 | Forgot password | EPP | 2023-03-22 | 2023-03-23 | 1 | 2023-03-30 | 2023-03-31 | 1 | 100%
|  | 14-4 | Logout | EPP | 2023-03-22 | 2023-03-23 | 1 | 2023-03-28 | 2023-03-29 | 1 | 100%
|  | 14-5 | HomePage Slider&Text | WMT | 2023-03-20 | 2023-03-21 | 1 | 2023-03-31 | 2023-04-01 | 1 | 100%
|  | 14-6 | About us | WMT | 2023-03-20 | 2023-03-21 | 1 | 2023-03-31 | 2023-04-01 | 1 | 100%
|  | 14-7 | Services | WMT | 2023-03-22 | 2023-03-23 | 1 | 2023-03-27 | 2023-03-28 | 1 | 100%
|  | 14-8 | Customer reviews | EPP | 2023-03-25 | 2023-03-26 | 1 | 2023-04-01 | 2023-04-02 | 1 | 100%
|  | 14-09 | Contactus | EPP | 2023-03-23 | 2023-03-24 | 1 | 2023-03-24 | 2023-03-25 | 1 | 100%
|  | 14-10 | Footer | WMT | 2023-03-22 | 2023-03-23 | 1 | 2023-03-27 | 2023-03-28 | 1 | 100%
|  | 14-11 | Shop header | WMT | 2023-03-22 | 2023-03-23 | 1 | 2023-04-04 | 2023-04-05 | 1 | 100%
|  | 14-12 | Trending cafe and food | EPP | 2023-03-20 | 2023-03-21 | 1 | 2023-04-06 | 2023-04-07 | 1 | 100%
|  | 14-13 | Trending shop | EPP | 2023-03-22 | 2023-03-23 | 1 | 2023-04-07 | 2023-04-08 | 1 | 100%
|  | 14-14 | Seemore(products) | AKM | 2023-03-23 | 2023-03-24 | 1 | 2023-04-01 | 2023-04-02 | 1 | 100%
|  | 14-15 | Seemore(shops) | EPP | 2023-03-24 | 2023-03-25 | 1 | 2023-04-06 | 2023-04-07 | 1 | 100%
|  | 14-16 | Promotions | EPP | 2023-03-30 | 2023-03-31 | 1 | 2023-04-07 | 2023-04-08 | 1 | 100%
|  | 14-17 | Seemore(promotion products) | EPP | 2023-03-24 | 2023-03-25 | 1 | 2023-04-08 | 2023-04-09 | 1 | 100%
|  | 14-18 | Buyshop | AKM | 2023-03-22 | 2023-03-23 | 1 | 2023-03-27 | 2023-03-28 | 1 | 100%
|  | 14-19 | Buy shop check | AKM | 2023-03-22 | 2023-03-23 | 1 | 2023-03-22 | 2023-03-23 | 1 | 100%
|  | 14-20 | Give shop dashboard | AKM | 2023-03-22 | 2023-03-23 | 1 | 2023-03-22 | 2023-03-23 | 1 | 100%
|  | 14-21 | KBZ pay scan | EPP | 2023-03-30 | 2023-03-31 | 1 | 2023-04-06 | 2023-04-07 | 1 | 100%
|  | 14-22 | Wave | AKM | 2023-03-25 | 2023-03-26 | 1 | 2023-04-07 | 2023-04-08 | 1 | 100%
|  | 14-23 | Search | AKM | 2023-03-28 | 2023-03-29 | 1 | 2023-04-07 | 2023-04-08 | 1 | 100%
|  | 14-24 | Buy products | AKM | 2023-03-24 | 2023-03-25 | 1 | 2023-03-27 | 2023-03-28 | 1 | 100%
|  | 14-25 | Favourite | AKM | 2023-03-24 | 2023-03-25 | 1 | 2023-04-06 | 2023-04-07 | 1 | 100%
|  | 14-26 | Cart | AKM | 2023-03-24 | 2023-03-25 | 1 | 2023-03-28 | 2023-04-02 | 5 | 100%
|  | 14-27 | Checkout | AKM | 2023-03-26 | 2023-03-27 | 1 | 2023-04-02 | 2023-04-03 | 1 | 100%
|  | 14-28 | Order confirm | AKM | 2023-03-26 | 2023-03-27 | 1 | 2023-04-02 | 2023-04-03 | 1 | 100%
|  | 14-29 | Calculate distance for delivery | AKM | 2023-03-26 | 2023-03-27 | 1 | 2023-04-02 | 2023-04-03 | 1 | 100%
|  | 14-30 | Comment and like section for blog | WMT | 2023-03-25 | 2023-03-26 | 1 | 2023-03-25 | 2023-03-26 | 1 | 100%
|  | 14-31 | Dashboard(profile) | EPP | 2023-03-27 | 2023-03-28 | 1 | 2023-03-28 | 2023-03-31 | 3 | 100%
|  | 14-32 | Dashboard(history_order) | AKM | 2023-03-27 | 2023-03-28 | 1 | 2023-04-03 | 2023-04-04 | 1 | 100%
|  | 14-33 | Dashboard(history_booking) | AKM | 2023-03-29 | 2023-03-30 | 1 |  |  | 0 | 100%
|  | 14-34 | Review | EPP | 2023-03-29 | 2023-03-30 | 1 | 2023-04-07 | 2023-04-08 | 1 | 100%
|  | 14-35 | Setting(change password) | EPP | 2023-03-30 | 2023-03-31 | 1 | 2023-03-30 | 2023-03-31 | 1 | 100%
|  | 14-36 | Contact us email system | EPP | 2023-03-28 | 2023-03-29 | 1 | 2023-03-23 | 2023-03-24 | 1 | 100%
|  | 14-37 | give coin | WMT | 2023-03-28 | 2023-03-29 | 1 |  |  | 0 | 100%
|  | 14-38 | Shop interface promotion menu | AKM | 2023-03-25 | 2023-03-26 | 1 | 2023-03-25 | 2023-03-26 | 1 | 100%
| 15 |  | Shop
|  | 15-1 | Login | AKM | 2023-03-26 | 2023-03-27 | 1 | 2023-03-22 | 2023-03-23 | 1 | 100%
|  | 15-2 | Logout | EPP | 2023-03-26 | 2023-03-27 | 1 | 2023-03-28 | 2023-03-29 | 1 | 100%
|  | 15-3 | Forget Password(get OTP) | EPP | 2023-03-26 | 2023-03-27 | 1 | 2023-03-30 | 2023-03-31 | 1 | 100%
|  | 15-4 | Forget password (change password) | EPP | 2023-03-26 | 2023-03-27 | 1 | 2023-03-30 | 2023-03-31 | 1 | 100%
|  | 15-5 | Sale chart | AKM | 2023-03-28 | 2023-03-29 | 1 | 2023-04-04 | 2023-04-05 | 1 | 100%
|  | 15-6 | History | AKM | 2023-03-29 | 2023-03-30 | 1 |  |  | 0 | 100%
|  | 15-7 | Order Page | WMT | 2023-03-29 | 2023-03-30 | 1 | 2023-04-06 | 2023-04-07 | 1 | 100%
|  | 15-8 | Booking | WMT | 2023-03-29 | 2023-03-30 | 1 | 2023-03-24 | 2023-03-25 | 1 | 100%
|  | 15-9 | Change Information | AKM | 2023-03-28 | 2023-03-29 | 1 | 2023-03-26 | 2023-03-27 | 1 | 100%
|  | 15-10 | Add & Change Blog | WMT | 2023-03-30 | 2023-03-31 | 1 | 2023-04-06 | 2023-04-07 | 1 | 100%
|  | 15-11 | Add Menu | AKM | 2023-03-29 | 2023-03-30 | 1 | 2023-03-29 | 2023-03-30 | 1 | 100%
|  | 15-13 | Discount | AKM | 2023-03-30 | 2023-03-31 | 1 | 2023-03-25 | 2023-03-26 | 1 | 100%
|  | 15-14 | Renewal Shop(Dashboard) | WMT | 2023-03-27 | 2023-03-28 | 1 | 2023-04-06 | 2023-04-07 | 1 | 100%
|  | 15-15 | Notification | AKM | 2023-03-28 | 2023-03-29 | 1 | 2023-03-23 | 2023-03-24 | 1 | 100%
|  | 15-16 | Gallery | EPP | 2023-03-28 | 2023-03-29 | 1 | 2023-03-27 | 2023-03-28 | 1 | 100%
|  | 15-17 | Update Menu | AKM | 2023-03-29 | 2023-03-30 | 1 | 2023-03-25 | 2023-03-26 | 1 | 100%
| 16 |  | Admin
|  | 16-1 | Shop List (Dashboard) | WMT | 2023-03-28 | 2023-03-29 | 1 | 2023-03-24 | 2023-03-25 | 1 | 100%
|  | 16-2 | Login | EPP | 2023-03-22 | 2023-03-23 | 1 | 2023-03-23 | 2023-03-24 | 1 | 100%
|  | 16-3 | User List (Dashboard) | WMT | 2023-03-22 | 2023-03-23 | 1 | 2023-04-03 | 2023-04-04 | 1 | 100%
|  | 16-5 | Home Slider (Dashboard) | WMT | 2023-03-22 | 2023-03-22 | 1 | 2023-03-28 | 2023-03-29 | 1 | 100%
|  | 16-6 | About (Dashboard) | AKM | 2023-03-22 | 2023-03-22 | 1 | 2023-03-28 | 2023-03-29 | 1 | 100%
|  | 16-7 | Service (Dashboard) | EPP | 2023-03-22 | 2023-03-22 | 1 | 2023-03-27 | 2023-03-28 | 1 | 100%
|  | 16-8 | Customer's Review (Dashboard) | EPP | 2023-03-23 | 2023-03-24 | 1 | 2023-04-02 | 2023-04-03 | 1 | 100%
|  | 16-9 | Choose options & fill | AKM | 2023-03-25 | 2023-03-26 | 1 | 2023-03-31 | 2023-04-01 | 1 | 100%
|  | 16-10 | Contact Us (Dashboard) | EPP | 2023-03-22 | 2023-03-23 | 1 | 2023-03-23 | 2023-03-24 | 1 | 100%
|  | 16-11 | PrivacyPolicy(Dashboard) | WMT | 2023-03-21 | 2023-03-22 | 1 | 2023-03-21 | 2023-03-22 | 1 | 100%
|  | 16-12 | FAQs(Dashboard) | WMT | 2023-03-21 | 2023-03-22 | 1 | 2023-03-22 | 2023-03-24 | 2 | 100%
|  | 16-15 | Footer | EPP | 2023-03-22 | 2023-03-22 | 1 | 2023-03-27 | 2023-03-28 | 1 | 100%
|  | 16-16 | Logout | EPP | 2023-03-22 | 2023-03-23 | 1 | 2023-03-28 | 2023-03-29 | 1 | 100%
0%
363
[6 empty] | Month | 12.1
T_CU_Coin
| customer_id | Customer ID
| coin | Coin Balance
| approve_By | Approve By
Note on E187: ====== ID#AAAArSosZQ8 Aung kaung Moe (2023-03-19 16:57:33) get home page slider & text from admin changes
Note on E188: ====== ID#AAAArSosZRA Aung kaung Moe (2023-03-19 16:58:12) get home page about us from admin changes
Note on E189: ====== ID#AAAArSosZRE Aung kaung Moe (2023-03-19 16:58:55) get home page services from admin changes
Note on E190: ====== ID#AAAArSosZRI Aung kaung Moe (2023-03-19 17:00:10) get customers reviews from admin prove
Note on E191: ====== ID#AAAArSosZRM Aung kaung Moe (2023-03-19 17:00:58) get contact us from admin changes
Note on E192: ====== ID#AAAArSosZRQ Aung kaung Moe (2023-03-19 17:01:15) get home page footer from admin changes
Note on E193: ====== ID#AAAArSosZRU Aung kaung Moe (2023-03-19 17:02:41) get shop header from admin changes
Note on E194: ====== ID#AAAArSosZRY Aung kaung Moe (2023-03-19 17:03:21) admin will get top selling products from every shop and rearrange and show in trending food and cafe
Note on E195: ====== ID#AAAArSosZRc Aung kaung Moe (2023-03-19 17:03:51) admin will get top selling shop from every shop and rearrange and show in trending shop
Note on E196: ====== ID#AAAArSosZRg Aung kaung Moe (2023-03-19 17:04:50) getting all products from every shop's db
Note on E197: ====== ID#AAAArSosZRk Aung kaung Moe (2023-03-19 17:05:19) getting all shops from every db
Note on E198: ====== ID#AAAArSosZRo Aung kaung Moe (2023-03-19 17:06:08) get promotions slider/text/shop/products from admin changes
Note on E199: ====== ID#AAAArSosZRs Aung kaung Moe (2023-03-19 17:07:38) getting all promotion products from every db
Note on E200: ====== ID#AAAArSosZR0 Aung kaung Moe (2023-03-19 17:10:05) get buy shop header and shop option from admin changes
Note on E201: ====== ID#AAAArSosZR4 Aung kaung Moe (2023-03-19 17:10:58) checking login user for buy shop
Note on E202: ====== ID#AAAArSosdKw Aung kaung Moe (2023-03-19 17:14:14) giving dashboard with shop name
Note on E204: ====== ID#AAAArSosdK0 Aung kaung Moe (2023-03-19 17:15:37) fake wave, get otp code with gmail acc
Note on E206: ====== ID#AAAArSosdK4 Aung kaung Moe (2023-03-19 17:17:34) check login for product buy
Note on E219: ====== ID#AAAArSosdLA Aung kaung Moe (2023-03-19 17:25:52) give coin new sign up user and get coin from you bought productsl.

## Schedule (Person)
Schedule |  | CAFE | [41 empty] | Create Date
[44 empty] | Update Date | 2022-09-22
|  |  | Feb |  | March | [30 empty] | April
| No | Assign | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
| 1 | Aung Kaung Moe
| 2 | Chit Paing Soe
| 3 | Ei Pwint Phyo
| 4 | Chyu Yati
| 5 | Win Myat Thwe
Note on D6: ====== ID#AAAAsKStrgc Aung kaung Moe (2023-02-28 07:33:26) Screen List(User List & Shop Owner List) & Discussing UI Kit & Home page Design
Note on E6: ====== ID#AAAAsKStrgg Aung kaung Moe (2023-02-28 07:34:30) Screen List(Admin) & Function List & Discussing UI kits & Figma Design
Note on F6: ====== ID#AAAAsV_ZQmM Aung kaung Moe (2023-03-01 16:17:33) Contact Us & User Flowchart & UI Kits
Note on G6: ====== ID#AAAAsaXPM-k Aung kaung Moe (2023-03-03 06:14:38) BlogPage & PaymentShop & Buy Shop
Note on H6: ====== ID#AAAAqxEoCVU Aung kaung Moe (2023-03-04 14:56:27) shop owner dashboard frame
Note on I6: ====== ID#AAAAseWb-LI Aung kaung Moe (2023-03-05 13:25:16) shopownerdashboard
Note on J6: ====== ID#AAAAseWb-LE Aung kaung Moe (2023-03-05 13:24:52) wavePayment&ThemeSetting
Note on K6: ====== ID#AAAAson_Mp0 Aung kaung Moe (2023-03-10 12:48:49) search Bar/Fav
Note on L6: ====== ID#AAAAson_Mpw Aung kaung Moe (2023-03-10 12:47:31) rechecking figma design
Note on M6: ====== ID#AAAAsoXyhBM Aung kaung Moe (2023-03-10 04:50:10) prototype
Note on N6: ====== ID#AAAAsoXyhBI Aung kaung Moe (2023-03-10 04:49:38) res(blog,salechart,history,wavepay,buyshop,home, homesearch,fav,
Note on O6: ====== ID#AAAAssNTuhk Aung kaung Moe (2023-03-12 12:31:15) res(shop Dashboard(all))
Note on P6: ====== ID#AAAAssNTuho Aung kaung Moe (2023-03-12 12:31:32) root code
Note on Q6: ====== ID#AAAArEZL97A Aung kaung Moe (2023-03-14 09:04:20) Home Page
Note on R6: ====== ID#AAAArEZL97E Aung kaung Moe (2023-03-14 09:05:15) Home Page
Note on S6: ====== ID#AAAArNIF0eQ Aung kaung Moe (2023-03-15 04:39:44) fav,buyshop,fillshoppayment
Note on T6: ====== ID#AAAAtHzZgvM Aung kaung Moe (2023-03-16 15:41:33) dashboard(order,booking,history)
Note on U6: ====== ID#AAAAtHzhJxk Aung kaung Moe (2023-03-16 15:45:26) dashboard(notifications,informations,gallery,promotions,blog,shop,menu)
Note on V6: ====== ID#AAAArSosdLE Aung kaung Moe (2023-03-19 17:58:58) shop(theme)
Note on W6: ====== ID#AAAArSosdLI Aung kaung Moe (2023-03-19 17:59:17) shop(messageChatBox & sale chart)
Note on X6: ====== ID#AAAArSosdLM Aung kaung Moe (2023-03-19 17:59:37) User(review, notifications)
Note on Y6: ====== ID#AAAAsUvid-A Aung kaung Moe (2023-03-24 04:29:14) rechecking front end
Note on Z6: ====== ID#AAAAsUvid-E Aung kaung Moe (2023-03-24 04:29:56) responsive design, linking all page, filling the blank.
Note on AA6: ====== ID#AAAAsUvid98 Aung kaung Moe (2023-03-24 04:28:48) shop fill information
Note on AB6: ====== ID#AAAAsUvid94 Aung kaung Moe (2023-03-24 04:27:47) Shop Login, shop fill information, shop mail send
Note on AC6: ====== ID#AAAAt2pB__M Aung kaung Moe (2023-03-26 13:17:43) history,noti
Note on AD6: ====== ID#AAAAt2pB__I Aung kaung Moe (2023-03-26 12:45:14) add and promotion menu
Note on AE6: ====== ID#AAAAt2pB__E Aung kaung Moe (2023-03-26 12:44:16) update menu
Note on AF6: ====== ID#AAAAt30ASSs Aung kaung Moe (2023-03-27 13:55:44) information, delete menu
Note on AG6: ====== ID#AAAArkhyt84 Aung kaung Moe (2023-03-28 14:44:06) buy shop, products buy(check login), cart(30%)
Note on AH6: ====== ID#AAAAsCBwrcE Aung kaung Moe (2023-03-31 10:22:11) about us
Note on AI6: ====== ID#AAAAsCBwrcI Aung kaung Moe (2023-03-31 10:22:22) choose option and fill
Note on AJ6: ====== ID#AAAAu7hcLLY Ei Pwint Phyo (2023-04-09 07:00:32) Choose option and fill
Note on AK6: ====== ID#AAAAu7hcLLQ Ei Pwint Phyo (2023-04-09 06:58:25) cart
Note on AL6: ====== ID#AAAAu7hcLLc Ei Pwint Phyo (2023-04-09 07:01:09) checkout,order details
Note on AM6: ====== ID#AAAAu7hcLLs Ei Pwint Phyo (2023-04-09 07:04:11) checkout,orderConfirm,tmr fav calculate distance for delivery
Note on AO6: ====== ID#AAAAu7hcLL0 Ei Pwint Phyo (2023-04-09 07:05:27) sale chart
Note on AP6: ====== ID#AAAAu7hcLL8 Ei Pwint Phyo (2023-04-09 07:07:25) check all page
Note on G7: ====== ID#AAAAmYDCqHc Chyu Yati (2023-03-03 17:06:25) shop figma
Note on H7: ====== ID#AAAAmYDCqHg Chyu Yati (2023-03-03 17:06:40) promotion figma, shop figma
Note on I7: ====== ID#AAAAsc6zpjk Chyu Yati (2023-03-04 17:03:21) promotion figma, promotion menu figma , shop figma
Note on J7: ====== ID#AAAAquSx4Kc Chyu Yati (2023-03-05 07:24:22) user dashboard , user history , user review , user chatbox
Note on K7: ====== ID#AAAAsd8Q0PY Chyu Yati (2023-03-06 15:27:40) promotion shop figma, Translation
Note on L7: ====== ID#AAAAq0ysxjI Kyaw Kyaw (2023-03-07 12:47:32) Translation
Note on M7: ====== ID#AAAAsoQJMQ0 Kyaw Kyaw (2023-03-09 16:41:07) flowchart ( Translation )
Note on N7: ====== ID#AAAAsoQJMQ4 Kyaw Kyaw (2023-03-09 16:41:51) Userdashboard Mobile View
Note on O7: ====== ID#AAAAtV3Y9WY Kyaw Kyaw (2023-03-19 14:37:26) Translation
Note on P7: ====== ID#AAAAtV3Y9Wc Kyaw Kyaw (2023-03-19 14:38:04) Translation
Note on Q7: ====== ID#AAAAtV3Y9Wg Kyaw Kyaw (2023-03-19 14:38:27) Translation
Note on R7: ====== ID#AAAAtV3Y9Wk Kyaw Kyaw (2023-03-19 14:38:47) User Dashboard (Profile)
Note on S7: ====== ID#AAAAtV3Y9Wo Kyaw Kyaw (2023-03-19 14:39:28) User DashBoard (Profile)
Note on T7: ====== ID#AAAAtV3Y9Ws Kyaw Kyaw (2023-03-19 14:40:32) User DashBoard (Booking)
Note on U7: ====== ID#AAAAtV3Y9Ww Kyaw Kyaw (2023-03-19 14:40:57) User DashBoard(order)
Note on V7: ====== ID#AAAAtV3Y9W0 Kyaw Kyaw (2023-03-19 14:41:18) User DashBoard(review)
Note on D8: ====== ID#AAAAsJOy9Gw Ei Pwint Phyo (2023-02-27 14:14:43) Screen list(user screen list, shop screen list)
Note on E8: ====== ID#AAAAsGlEzcw Ei Pwint Phyo (2023-02-28 15:15:43) Screen List(Admin)&Function List
Note on F8: ====== ID#AAAAsV_ZQmE Ei Pwint Phyo (2023-03-01 15:41:47) User(login & Sign Up figma) Shop interface figma
Note on H8: ====== ID#AAAAsbD83FU Ei Pwint Phyo (2023-03-03 14:38:46) order page
Note on I8: ====== ID#AAAAseWb-LM Ei Pwint Phyo (2023-03-05 15:25:02) Shop interface(100%),Menu, forgot password , order ,cart ,Place order, popup, booking,
Note on K8: ====== ID#AAAAsoXyhBE Ei Pwint Phyo (2023-03-10 04:31:55) checking drive & mobile design
Note on O8: ====== ID#AAAArDGSFoI Ei Pwint Phyo (2023-03-13 12:37:17) checked function list
Note on P8: ====== ID#AAAArDGSFoM Ei Pwint Phyo (2023-03-13 12:38:09) checked all list
Note on Q8: ====== ID#AAAArDGSFoQ Ei Pwint Phyo (2023-03-13 12:41:00) forgot password(2 page),sign in,login(user,admin,shop)all 80%, booking 60%
Note on S8: ====== ID#AAAArsHf1gI Ei Pwint Phyo (2023-03-15 13:12:36) forgot password(2 page),sign in,login(user,admin,shop)all 95%, booking 65%
Note on T8: ====== ID#AAAArsHf1gM Ei Pwint Phyo (2023-03-15 13:12:51) booking 85%
Note on U8: ====== ID#AAAAtVLYsPs Ei Pwint Phyo (2023-03-19 12:36:08) shop interface & check all
Note on W8: ====== ID#AAAAtVLYsPw Ei Pwint Phyo (2023-03-19 12:36:50) shopinterface & checkout
Note on Y8: ====== ID#AAAAuabpA1w Ei Pwint Phyo (2023-03-31 14:46:36) login,signup
Note on AA8: ====== ID#AAAAuabpA2c Ei Pwint Phyo (2023-03-31 14:51:59) sign up & login 100%
Note on AB8: ====== ID#AAAAuabpA2Y Ei Pwint Phyo (2023-03-31 14:51:39) admin login
Note on AC8: ====== ID#AAAAuabpA2g Ei Pwint Phyo (2023-03-31 14:52:39) contact us dashboard
Note on AD8: ====== ID#AAAAuabpA2U Ei Pwint Phyo (2023-03-31 14:51:00) log out & services
Note on AE8: ====== ID#AAAAuabpA2Q Ei Pwint Phyo (2023-03-31 14:50:33) gallery
Note on AF8: ====== ID#AAAAuabpA2M Ei Pwint Phyo (2023-03-31 14:50:13) footer & gallery
Note on AG8: ====== ID#AAAAuabpA2E Ei Pwint Phyo (2023-03-31 14:49:46) contact us email
Note on AH8: ====== ID#AAAAuabpA2A Ei Pwint Phyo (2023-03-31 14:49:08) userdashboard profile
Note on AI8: ====== ID#AAAAuabpA10 Ei Pwint Phyo (2023-03-31 14:48:08) forgotpassword
Note on AJ8: ====== ID#AAAAuabpA14 Ei Pwint Phyo (2023-03-31 14:48:32) forgot password user and shop ------ ID#AAAAuabpA18 Ei Pwint Phyo (2023-03-31 14:48:54) and change password
Note on AK8: ====== ID#AAAAu7hcLLU Ei Pwint Phyo (2023-04-09 06:59:25) change password,forgot password,star rating. admin review
Note on AM8: ====== ID#AAAAu7hcLLk Ei Pwint Phyo (2023-04-09 07:03:01) log out popup, customer review,promotion
Note on AP8: ====== ID#AAAAu7hd-fE Ei Pwint Phyo (2023-04-09 07:08:06) check all page
Note on D9: ====== ID#AAAAsJOy9Gs Chyu Yati (2023-02-27 14:14:26) Screen list ( shop screen list )
Note on E9: ====== ID#AAAAsFiLP_U Chyu Yati (2023-02-28 04:05:56) screen list (admin)
Note on F9: ====== ID#AAAAsV_ZQmI Chyu Yati (2023-03-01 16:11:50) admin flowchart, user flowchart, home flowchart
Note on G9: ====== ID#AAAAmYDCqHY Chyu Yati (2023-03-03 17:06:01) promotion figma
Note on H9: ====== ID#AAAAmYDCqHU Chyu Yati (2023-03-03 17:05:49) promotion figma, and shop figma
Note on I9: ====== ID#AAAAsc6zpjg Chyu Yati (2023-03-04 17:03:14) promotion figma, promotion menu figma , shop figma
Note on J9: ====== ID#AAAAquSx4Kg Chyu Yati (2023-03-05 07:24:29) user dashboard , user history , user review , user chatbox
Note on K9: ====== ID#AAAAsd8Q0PU Chyu Yati (2023-03-06 15:27:14) promotion shop figma
Note on L9: ====== ID#AAAAq-d4-cs Chyu Yati (2023-03-08 14:04:37) database design
Note on M9: ====== ID#AAAAq-d4-bY Chyu Yati (2023-03-08 13:53:33) database design
Note on N9: ====== ID#AAAAsoQJMQ8 Kyaw Kyaw (2023-03-09 16:41:56) Userdashboard Mobile View
Note on O9: ====== ID#AAAAsrNERAo Chyu Yati (2023-03-11 16:13:16) database design
Note on P9: ====== ID#AAAAsrNERAs Chyu Yati (2023-03-11 16:15:46) database, er diagram
Note on Q9: ====== ID#AAAArOjRlsk Chyu Yati (2023-03-16 12:52:15) promotion page(20%)
Note on S9: ====== ID#AAAArOjRlss Chyu Yati (2023-03-16 12:55:14) promotion 50%
Note on T9: ====== ID#AAAArOjRlso Chyu Yati (2023-03-16 12:52:39) promotion product menu(100%)
Note on U9: ====== ID#AAAArOjRlsw Chyu Yati (2023-03-16 12:55:41) promotion shop menu(100%) , shop list (10%)
Note on V9: ====== ID#AAAArTE6F-I Chyu Yati (2023-03-20 12:50:45) shoplist (95%) complete
Note on X9: ====== ID#AAAArTE6F-E Chyu Yati (2023-03-20 12:50:13) fix (promotion page code)
Note on Z9: ====== ID#AAAAtc9KRpg Chyu Yati (2023-03-22 06:22:18) fontend checking
Note on D10: ====== ID#AAAArz71Ogw Thwe Lay (2023-02-27 16:26:32) Screen List (User Screen List), Requirement_Definition
Note on E10: ====== ID#AAAAsGlEzc0 Thwe Lay (2023-02-28 15:27:03) Screen List(Admin Screen), Function List
Note on F10: ====== ID#AAAAsXeq8Do Thwe Lay (2023-03-02 15:22:30) Dashboard(User List)
Note on G10: ====== ID#AAAAq-d4-bQ Thwe Lay (2023-03-08 12:21:16) Slider, About, Service, Customer's Review ------ ID#AAAAq-d4-bU Thwe Lay (2023-03-08 12:22:39) Contact Us, Theme & Font
Note on J10: ====== ID#AAAAq-d4-bM Thwe Lay (2023-03-08 12:18:25) (Dashboard)Chat Box, Choose Options & fills, User Guide, FAQs
Note on L10: ====== ID#AAAAq-d4-bI Thwe Lay (2023-03-08 12:16:43) Discount & Promotions
Note on M10: ====== ID#AAAAsoQJMRA Thwe Lay (2023-03-09 16:47:45) Database, Figma
Note on N10: ====== ID#AAAAsoQJMRE Thwe Lay (2023-03-09 16:48:02) Responsive Figma Design
Note on O10: ====== ID#AAAAsrNERA0 Thwe Lay (2023-03-11 16:51:47) database
Note on P10: ====== ID#AAAAsrNERA4 Thwe Lay (2023-03-11 16:51:56) database
Note on R10: ====== ID#AAAArDGSFoE Thwe Lay (2023-03-13 12:07:34) PrivacyPolicy, FAQs
Note on S10: ====== ID#AAAArEZL974 Thwe Lay (2023-03-14 11:00:26) Admin Dashboard
Note on V10: ====== ID#AAAAu7hd-fI Thwe Lay (2023-04-09 09:39:54) Kbz,confirm,payment Popup
Note on Y10: ====== ID#AAAArg5WFn0 Thwe Lay (2023-03-24 08:15:22) Kbz,confirm,payment Popup
Note on Z10: ====== ID#AAAArg5WFnw Thwe Lay (2023-03-24 08:14:59) Database
Note on AA10: ====== ID#AAAArg5WFns Thwe Lay (2023-03-24 08:14:48) Database
Note on AB10: ====== ID#AAAArg5WFnk Thwe Lay (2023-03-24 08:10:53) PrivacyPolicy
Note on AC10: ====== ID#AAAArg5WFno Thwe Lay (2023-03-24 08:11:03) FAQs
Note on AD10: ====== ID#AAAAt2pB__A Thwe Lay (2023-03-26 12:42:50) Shop List, Booking
Note on AE10: ====== ID#AAAAt2pB_-8 Thwe Lay (2023-03-26 12:42:10) Blog
Note on AF10: ====== ID#AAAAu7hcLLE Ei Pwint Phyo (2023-04-09 06:53:26) wave pay
Note on AG10: ====== ID#AAAAu7hcLLI Ei Pwint Phyo (2023-04-09 06:53:56) Footer & Services (user)
Note on AH10: ====== ID#AAAAu7hcLLM Ei Pwint Phyo (2023-04-09 06:54:20) Home slider
Note on AI10: ====== ID#AAAAsCH2xp0 Thwe Lay (2023-04-02 04:03:40) aboutus
Note on AJ10: ====== ID#AAAAsCH2xps Thwe Lay (2023-04-02 04:03:24) coins dashboard
Note on AK10: ====== ID#AAAAsCH2xpw Thwe Lay (2023-04-02 04:03:34) slidertext ------ ID#AAAAu7hcLLg Ei Pwint Phyo (2023-04-09 07:02:28) wave page 1
Note on AM10: ====== ID#AAAAu7hcLLo Ei Pwint Phyo (2023-04-09 07:03:44) user list & shop header
Note on AN10: ====== ID#AAAAu7hcLLw Ei Pwint Phyo (2023-04-09 07:04:59) add and changes blog
Note on AO10: ====== ID#AAAAu7hcLL4 Ei Pwint Phyo (2023-04-09 07:06:00) Trending cafe and food.
Note on AP10: ====== ID#AAAAu7hcLMA Ei Pwint Phyo (2023-04-09 07:07:57) check all page

## Requirement Definition
Requirement_Definition | 0 | Create Date
|  | Update Date | 2023-04-11 23:13
１.Business Requirement
１−１. System Background
With the hectic schdeule nowadays, sometimes it is hard to go out and buy your favouirite coffee, drinks and foods.With this system, even when you are too busy or too lazy to go out, you can buy any food and drinks without going anywhere and safe from rain and sun.One stop solution place for Couple, for business people,for teenagers who are looking for a place to meet.
１−2.Target Point Of System
This is to gather the all the Coffee Shops in the Yangon in one place and with one click, a user can buy the food,drinks with delievery system. It also helps increasing the sales of the shops.This website target customers include all kind of ages.
１−3.After System Changes Flow
Once this website is developed, Shops can regularly update information on food products without communicatingwith the customers unlike Social Media.Instocks can be seen in real time. Review system encourages them to do better on business. The customers will have information on the shops inthrough the website, can order available food faster and no call is needed. The user can check the delivery and estimated arrival time can be known.
2.Function Definition
2−１.System Definition
With this system, Shops will have a lot of take away orders and it will increase the sales in a way and saves time from taking order. As the online payment system is also used, collectiong the payment is optional. They can decorate their own page depends on their purchased package Limit. With this system, Users have a variety of Shops and Drinks and Food Products to choose from. Cash or return change is no longer needed with online payment.

## 要件定義
要件定義 | CAFE |  | 作成日
|  |  | 更新日 | 2023-04-11 23:13
１.ビジネス要件
１−１. システムの背景
| 今日の多忙なスケジュールにより、外に出てコーヒー、飲み物、食べ物を買うことが困難になることがあります。そのため、このシステムがあれば、忙しくて外出するのが面倒な場合でも、どこにも行かなくても安全に食べ物を買うことができます。カップルのためのロマンチックな場所、ビジネスミーティングのための静かな場所 、ティーンエイジャーの写真を撮るのに最適な場所です。 | 目的 /在宅勤務 / カップル / 会社員
１−2.システムの目標
| ヤンゴンのすべてのコーヒー ショップが 1 か所に集められており、ユーザーはクリック しで、デリバリー システムを通じて食品を購入して使用することができます。このシステムにより、喫茶店の売り上げを伸ばし、配達員の収入を増やすことができます。このウェブサイトは、すべての年齢のユーザーを対象としています。 | システムは何を対象とするか
１−3.システム変更後のフロー
| このサイトが導入されると、店舗は通常の顧客とのコミュニケーションを必要とせずに、ソーシャル メディアで食品情報を更新できるようになります。食材の在庫がリアルタイムでわかる。繁忙期はご注文を締め切らせていただく場合がございます。 レビューシステムは、店舗がより良いビジネスを行うことを奨励します。 ユーザーは、お店の情報を 1 か所で入手できます。ユーザー ウェブサイトから直接座席を予約できます。ユーザーは電話をかけなくても、すぐに注文できます。ユーザーが確認できる 配達と到着予定時刻を知ることができます。 | システム導入後の現実世界の変化と効果
2.関数定義
2−１.システム定義
| お客様は店舗に行かなくても、このウェブサイトから注文できます。こうすることで 注文から時間を節約し、売り上げを伸ばす。支払いはユニット単位で行うため、集金の必要はありません。 ショップ インターフェースは自己管理可能なので、自分のページを無制限に装飾できます。 このシステムにより、顧客はさまざまなショップから飲み物や食べ物を選ぶことができます。 単位払い制ですので、返金の必要はありません。購入ポイントは合計購入時間金額に基づいて加算されます。 貯まったポイントは、割引商品の通貨として交換できます。 | 各機能の利点